## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Ruchira : An Assistive Platform to Empower Home Sellers |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A.P SHAH INSTITUE OF TECHNOLOGY, IT
PROJECT GUIDE |  | PROF. GANESH GOURSHETE |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Anita,Shifa,Harshita | 2020-01-20 | 2020-02-08 | 3 | 100% | bar: WEEK 1 F to WEEK 2 F
1.1.1 | Research paper finalization | Anita,Shifa | 2020-02-08 | 2020-02-26 | 3 | 100% | bar: WEEK 2 W to WEEK 2 F
1.2 | Project Title | Anita,Shifa,Harshita | 2020-02-28 | 2020-03-12 | 3 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Abstract | Anita | 2020-03-13 | 2020-03-30 | 2 | 100% | bar: WEEK 2 W to WEEK 3 R
1.4 | Objectives | Shifa | 2020-04-01 | 2020-04-15 | 2 | 100% | bar: WEEK 2 W to WEEK 3 R
1.5 | Literature Review | Anita,Shifa,Harshita | 2020-05-16 | 2020-05-30 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 3 T to WEEK 3 R
1.6 | Problem Definition | Harshita | 2020-06-01 | 2020-07-15 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 3 F
1.7 | Scope | Anuja | 2020-06-16 | 2020-06-22 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 3 F
1.8 | Technology stack | Shifa | 2020-06-23 | 2020-06-30 | 1 | 70% | bar: WEEK 2 W to WEEK 2 F; WEEK 3 F
1.9 | Benefits for environment | Harshita | 2020-07-01 | 2020-07-08 | 1 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 3 F
1.1 | Benefits for society | Harshita | 2020-07-09 | 2020-08-20 | 2 | 80% | bar: WEEK 2 W to WEEK 2 F; WEEK 3 F
1.11 | Applications | Anita,Shifa,Harshita | 2020-07-21 | 2020-08-30 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F; WEEK 3 F
2 | Project Design
2.1 | Proposed System | Anita,Shifa,Harshita | 2020-09-19 | 2020-09-27 | 1 | 70% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 M to WEEK 4 R
2.2 | Design(Flow Of Modules) | Anita,Shifa,Harshita | 2020-09-19 | 2020-09-27 | 1 | 70% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 F to WEEK 5 F
2.3 | Activity Diagram | Shifa | 2020-09-19 | 2020-09-27 | 1 | 50% | bar: WEEK 2 W to WEEK 2 F
2.4 | Use Case Diagram | Anita | 2020-09-19 | 2020-09-27 | 1 | 50% | bar: WEEK 2 W to WEEK 2 F
2.5 | Description Of Use Case |  | 2020-09-19 | 2020-09-27 | 1 | 30% | bar: WEEK 2 W to WEEK 2 F
2.6 | Modules |  |  |  | 1 | bar: WEEK 2 W to WEEK 2 F
2.6.1 | Module-1 | Anita,Shifa,Harshita | 2020-09-19 | 2020-09-27 | 1 | 50% | bar: WEEK 2 W to WEEK 2 F
2.6.2 | Module-2 | Harshita | 2020-09-19 | 2020-09-27 | 1 | 50% | bar: WEEK 2 W to WEEK 2 F
2.6.3 | Module-3 | Anita,Harshita | 2020-09-19 | 2020-09-27 | 1 | 30% | bar: WEEK 2 W to WEEK 2 F
2.6.4 | Module-4 | Harshita,Shifa | 2020-09-19 | 2020-09-27 | 1 | 20% | bar: WEEK 2 W to WEEK 2 F
2.7 | Preparation Of Report | Anita,Shifa,Harshita | 2020-09-19 | 2020-09-27 | 1 | 80% | bar: WEEK 2 W to WEEK 2 F
3 | Project Implementation
3.1 | Module-1 | Anita,Shifa,Harshita | 2021-02-04 | 2021-02-04 | 0 | 100% | bar: WEEK 2 W to WEEK 2 F
3.2 | Module-2 | Anuja | 2021-02-05 | 2021-02-05 | 0 | 100% | bar: WEEK 2 W to WEEK 2 F
3.3 | Module-3 | Shifa | 2021-02-11 | 2021-02-12 | 0 | 100% | bar: WEEK 2 W to WEEK 2 F
3.4 | Module-4 | Harshita | 2021-02-25 | 2021-02-26 | 0 | 80% | bar: WEEK 2 W to WEEK 2 F
4 | Testing
4.1 | Design of Test Cases | Anita,Shifa,Harshita | 2020-01-07 | 2020-01-24 | 3 | 40% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 T to WEEK 2 F; WEEK 3 T to WEEK 3 F
4.2 | Architecture | Anita,Shifa,Harshita | 2020-01-27 | 2020-02-03 | 1 | 40% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 W to WEEK 2 F
4.3 | Prototyping | Anita,Shifa,Harshita | 2020-02-04 | 2020-02-10 | 1 | 50% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 W to WEEK 2 F
4.4 | Devlopment | Harshita | 2020-02-11 | 2020-02-17 | 1 | 30% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 W to WEEK 2 F
4.5 | Installation and setting up of Darknet | Anita,Shifa,Harshita | 2020-02-18 | 2020-02-24 | 1 | 60% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 W to WEEK 2 F
5.1 | Report Preparation | Anita,Shifa,Harshita |  |  |  | 80% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 W to WEEK 2 F